## Sheet1
www.goodoldmanoj.com
Burn down chart
Project | Story | Task | Start | 2014-05-26 | 2014-05-27 | 2014-05-28 | 2014-05-29 | 2014-05-30 | 2014-05-31 | 2014-06-02 | 2014-06-03 | 2014-06-04 | 2014-06-05 | 2014-06-06 | 2014-06-07
My Project | Merancang cover |  | 3 | 1 | 0 | 0
My Project | Membuat pengantar |  | 2 | 1 | 0 | 0
My Project | Membuat list spesial efek film (daftar isi) |  | 3 | 1 | 0 | 0
My Project | Mengatur transisi slide |  | 4 | 2 | 0 | 0
My Project | Mendeskripsikan spesial efek "Stop Action" |  | 6 | 6 | 5 | 1
My Project | Mendeskripsikan spesial efek "In Camera Matte" |  | 6 | 6 | 6 | 6
My Project | Mendeskripsikan spesial efek "Glass Shot" |  | 6 | 6 | 6 | 6
My Project | Mendeskripsikan spesial efek "Travelling Matte" |  | 6 | 6 | 6 | 6
My Project | Mendeskripsikan spesial efek "Matte Pinting" |  | 6 | 6 | 6 | 6
My Project | Mendeskripsikan spesial efek "Wiliam Process" |  | 6 | 6 | 6 | 6
My Project | Mendeskripsikan spesial efek "Schufftan Process & Rear Projection |  | 6 | 6 | 6 | 6
My Project | Mendeskripsikan spesial efek "Cloud Tank" |  | 6 | 6 | 6 | 6
My Project | Mendeskripsikan spesial efek "Motion Control" |  | 6 | 6 | 6 | 6
My Project | Mendeskripsikan spesial efek "Front Projection" |  | 6 | 6 | 6 | 6
My Project | Mendeskripsikan spesial efek "Zoptics" |  | 6 | 6 | 6 | 6
My Project | Mendeskripsikan spesial efek "Electronic Composite" |  | 6 | 6 | 6 | 6
My Project | Mendeskripsikan spesial efek "Introvision" |  | 6 | 6 | 6 | 6
My Project | Mendeskripsikan spesial efek "3D Computer Graphics in a Composite" |  | 6 | 6 | 6 | 6
My Project | Mendeskripsikan spesial efek "Live-Action 3D" |  | 6 | 6 | 6 | 6
My Project | Membuat Ringkasan |  | 2 | 2 | 2 | 2
Ideal - Remaining efforts in uninterrupted working hours |  |  | 104 | 95 | 86 | 77 | 68 | 59 | 50 | 41 | 32 | 23 | 14 | 5 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  | 104 | 97 | 91 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on G5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on H5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered